## Dashboard
Task Status | Brenda C | Brian B | Cliff N | Evans W | Irine M | Joel M | Ken W | Sheilla W | Duncan M | Ivy N | Susan B | Solomon O |  | Total | %
Done | 31 | 28 | 26 | 12 | 26 | 24 | 32 | 26 | 56 | 25 | 28 | 11 | 0 | 325 | 84.64%
Ongoing | 7 | 3 | 6 | 2 | 2 | 3 | 1 | 2 | 2 | 5 | 4 | 1 | 0 | 38 | 9.896%
Pending | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 0.7812%
Not started | 1 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1.562%
Dropped | 4 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 12 | 3.125%
Total Tasks | 43 | 32 | 33 | 20 | 28 | 29 | 34 | 28 | 60 | 31 | 33 | 13 | 0 | 384 | 100%
Count | 43 | 32 | 33 | 20 | 28 | 29 | 34 | 28 | 60 | 31 | 33 | 13 | 0 | 384
Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Task Tracker
Project/ Client/ Investor | Action Point | Source | Status | Deadline | Owner | Assist | Notes
02 February - 06 February 2026
Sunset Diani Beach | Send Contract and NDA |  | Done | 2026-02-06 | Ken W
Jarine, Autospring, Transafrica Water | Duncan to coordinate with deal leads |  | Done | 2026-02-06 | Duncan M
Woodhall | Add on tracker |  | Done | 2026-02-06 | Duncan M
Yula | Grant access to VDR and check on the valuation expectations with the founder |  | Done | 2026-02-06 | Cliff N | Sheilla W
Project Nitrogen, Radium, Curious, agate and manganese | Send to Ola Edenbridge |  | Done | 2026-02-06 | Brenda C
Okke | Send Information on ISM Africa |  | Done | 2026-02-06 | Duncan M
Greenforest | Respond to Email revise amount to 500k usd |  | Done | 2026-02-06 | Cliff N
Yongeza | Do a write up on closed deal |  | Done | 2026-02-06 | Ivy N
St Brigits hospital | Irine to share deal with Nelly |  | Done | 2026-02-06 | Irine M
Encore medics ltd | Put on tracker |  | Done | 2026-02-06 | Ken W
Eatfresh | Put on tracker |  | Done | 2026-02-06 | Ken W
Women international | Follow up on data |  | Done | 2026-02-06 | Ivy N
Friend,Tunisia | Susan to review |  | Done | 2026-02-06 | Susan B
Kashia | Start on valuation |  | Done | 2026-02-06 | Sheilla W
Jacksos shona | Introduce him to yongeza |  | Done | 2026-02-06 | Cliff N
Tip point | Check if funds were received |  | Done | 2026-02-06 | Duncan M
Jarine | Check with SPE Capital |  | Done | 2026-02-06 | Brian B
Yongeza | Speak to Derrick On Yongeza Debt |  | Done | 2026-02-06 | Cliff N
Progressive,DT,Greenforest | Prepare deal of the weeks update |  | Done | 2026-02-06 | Ivy N
Diani beach | revise the contract fro 2% to 3% success fee |  | Done | 2026-02-06 | Susan B
Abler Nordic | Review termsheet |  | Done | 2026-02-06 | Evans W
Jackson | Send updated numbers for proteq |  | Done | 2026-02-06 | Brenda C
Double den | Confirm the address,rewrite as its from CEEC |  | Done | 2026-02-06 | Duncan M
COSEF | sign NDA |  | Done | 2026-02-06 | Duncan M
Karanja of KG Mills | follow up on contract |  | Done | 2026-02-06 | Ken W
Sidian | Follow up on engagement contract |  | Done | 2026-02-06 | Evans W
Farm Base feeds | Add on tracker |  | Done | 2026-02-06 | Ken W
Donald | Send teasers of projects shared on linked |  | Done | 2026-02-06 | Joel M
Global Capital BV | Save in folder |  | Done | 2026-02-06 | Joel M
Derrick | Data room Access |  | Done | 2026-02-06 | Cliff N
Gaia Impact | send deals on Solar energy and mini grids |  | Done | 2026-02-06 | Duncan M
Gaia Impact | Send ecocan deal |  | Done | 2026-02-06 | Ivy N
Crown | Add to legatics |  | Done | 2026-02-06 | Sheilla W
Gladys /Cider-vine | To be called by Ken,shes seeking a valuation |  | Done | 2026-02-06 | Ken W
PURA | Susan to update the teaser to mention that they are open to both debt and equity. |  | Done | 2026-02-06 | Susan B
Spice world | Cliff to follow up on the engagement contract. Susan to add the Tz entity to the live deal tracker |  | Done | 2026-02-06 | Cliff N |  | Pending retainer pyt
Tripple F | Client to share the correct set of accounts before NC starts on the assignments |  | Done | 2026-02-06 | Ken W |  | Not progressing with deal
Tigoni | follow up with client to provide data |  | Done | 2026-02-06 | Brian B
Sotik Assignment | Brenda is supposed to travel to Sotik in the 2nd week of Feb |  | Dropped | 2026-02-06 | Brenda C |  | followed up on email
MCB: | DM to follow up with Burak on the arrangements |  | Done | 2026-02-06 | Duncan M
CREAN | follow up with the client to pay retainer fees on the IM |  | Done | 2026-02-06 | Sheilla W
Valley Hospital: | check with Enko if they can fund them |  | Done | 2026-02-06 | Sheilla W
South B: | follow up on whether the payment has been made |  | Done | 2026-02-06 | Sheilla W
Crown Healthcare: | follow up on closure of the transaction |  | Done | 2026-02-06 | Sheilla W
Africa50: | Follow up |  | Done | 2026-02-06 | Duncan M
Vicky | Send FTG to Vicky from South Africa |  | Done | 2026-02-06 | Duncan M
Sealtowers: | Seek update form Axian |  | Done | 2026-02-06 | Duncan M
KDL: | reach out for 2025 number. Follow up with Kevin Kuria Absa and KCB |  | Done | 2026-02-06 | Duncan M
BB Finance: | Follow up for their feedback on Edenbridge |  | Done | 2026-02-06 | Brenda C
NWH: | Update NWH IM and send it to Dr. Thenya |  | Done | 2026-02-06 | Duncan M
Double den | KCB on double den |  | Done | 2026-02-06 | Duncan M
Timeless Timber: | Susan to add deal on the tracker |  | Done | 2026-02-06 | Susan B
09 February - 13 February 2026
Enat Bank TOR | Ken and Duncan to coordinate |  | Dropped | 2026-02-13 | Duncan M | Ken W | The Ethiopian company did not win the bid
Jarine | Share Management Accounts |  | Done | 2026-02-13 | Brian B
So Pure | Share data list |  | Done | 2026-02-13 | Susan B
Paytech | prepare a 10 paged concept note |  | Done | 2026-02-13 | Sheilla W
Stan | Share NDA |  | Done | 2026-02-13 | Ivy N
Premeir credit | create NDA and engagement contract |  | Done | 2026-02-13 | Ken W
IDH.ORG | share proposal. Submit proposal as is |  | Done | 2026-02-13 | Irine M
16 February - 20 February 2026
Enterprise France | Apply for funding for reclaim and post on linked in |  | Done | 2025-02-20 | Ivy N
Cider Vine | Work on valuation proposal |  | Done | 2025-02-20 | Ken W
Greenforest | Do computations on the termsheet |  | Done | 2025-02-20 | Ivy N
East river | Attend meeting |  | Done | 2025-02-20 | Ivy N
Enterprise Finance ltd | Prepare an NDA |  | Done | 2025-02-20 | Cliff N
Cool catch | Apply for grant |  | Done | 2025-02-20 | Brian B
Swift credit | Follow up on data request |  | Done | 2025-02-20 | Cliff N
23 February - 27 February 2026
Family Diet: | Deactivate VDR link for Inua Capital |  | Done | 2025-02-27 | Cliff N
Grei SEZ | Get docs on govt approval,land title and ask for feasibility,share docs with afrexim Bank studies in march 2026 |  | Done | 2025-02-27 | Cliff N
Classic Mouldings | Organize follow-up site visit for Humphrey and Wasilwa |  | Done | 2025-02-27 | Joel M
Umoja MFI | Follow up with EQ on 2nd Disbursement |  | Done | 2025-02-27 | Duncan M
Umoja MFI | Get group level financials from Mark |  | Done | 2025-02-27 | Duncan M
Tip Point: | Bank the postdated cheque from the client |  | Done | 2025-02-27 | Ken W
VCB | - Incred Insights DD |  | Done | 2025-02-27 | Duncan M |  | Wladi wants to push the DD to Sep 2026
So Pure | Complete financial model |  | Done | 2025-02-27 | Susan B |  | Should be So Pure
MyCredit | Complete valuation for Zahari and Zazipay. Follow up with the management to get financial projections and strategic plan/business plan for the equity valuations. |  | Done | 2025-02-27 | Duncan M
Kashia: | Complete the valuation. |  | Done | 2025-02-27 | Sheilla W
New palea | - Share deal with Fulton of BluePeak |  | Done | 2025-02-27 | Brenda C |  | we will pass on it due to its relatively small scale of only $35 million in revenue and its exclusive focus on Kenya.
U&I: | Brenda to follow up with the client for the 2025 accounts |  | Done | 2025-02-27 | Brenda C
Proteq Automation | Brenda, Ken- Disbursement is due this week |  | Done | 2025-02-27 | Brenda C |  | Due 0n 23rd March
Edenbridge: | Complete form for AECF |  | Done | 2025-02-27 | Brenda C
Savannah Hospital: | Review financials to assess whether it’s a good fit as our client |  | Done | 2025-02-27 | Brian B
Ravensus: | - Provide responses to Anna’s Qs (BLAO) |  | Done | 2025-02-27 | Sheilla W
Sunset Villa: | - Duncan to share Ahmed’s contact (Kanini Haraka affiliate) |  | Done | 2025-02-27 | Susan B
Spiceworld: | Add deal with on the Live Deal Tracker |  | Done | 2025-02-27 | Susan B |  | Completd first draft, reviews ongoing
Spiceworld: | Susan & Irine- BioInvest has requested for a financial model, Susan to work on the FM. Organize physical meeting with Cygnum. Firm up meeting with AgDevco |  | Done | 2025-02-27 | Susan B |  | Financial model ongoing
| Advisory Work Tracker: |  | Done | 2025-02-27 | Ken W
Tz Deals | Duncan to follow-up on the meetings we had. Also follow up on the meetings we missed and schedule virtual calls. |  | Done | 2025-02-27 | Duncan M
Swift | Cliff to visit Swift to finalize on requested information |  | Done | 2025-02-27 | Cliff N
Rafode | Evans to follow up on Rafode on defaulted |  | Done | 2025-02-27 | Evans W
E&M Tech | Duncan schedule a call with E&M Tech investor is interested |  | Done | 2025-02-27 | Duncan M
Umoja MFI | Umoja second disburse, follow up on 17th with rose – Duncan |  | Done | 2025-02-27 | Duncan M
Aplite | Do an NDA |  | Done | 2025-02-27 | Ken W
Mara Elephant | seeking valuation services |  | Done | 2025-02-27 | Ken W
ISM | Grant application |  | Dropped | 2025-02-27 | Ivy N
Umoja International | Engagement Contract |  | Done | 2025-02-27 | Ken W |  | Put on hold since the client is insisting on 0.5% success fees
Ecocan | Work on an update. Do Noblestride linkedIn deal announcement. Do after the client announces |  | Ongoing | 2025-02-27 | Ivy N |  | MD to advise
Kuria | Send cool catch deck |  | Done | 2025-02-27 | Brian B |  | Investor passed on the opportunity as it is not their field of expertise
Von KWFT | Send deck and financials |  | Done | 2025-02-27 | Brenda C
So Pure | Model Draft |  | Done | 2025-02-27 | Susan B
Kenneth | Greenforest teaser |  | Done | 2025-02-27 | Ivy N
Dhruv | Review FY25 accounts |  | Done | 2025-02-27 | Duncan M
Classic Mouldings | Site Visit,Business plan, |  | Done | 2025-02-27 | Joel M
2 March - 6 March 2026 |  |  |  | 2026-03-06
Ravensus | Complete info on the live deal tracker |  | Done | 2026-03-06 | Sheilla W
DT Logistics | Complete info on the live deal tracker. Joel to merge financials |  | Done | 2026-03-06 | Joel M
Progressive credit | Complete info on the live deal tracker |  | Done | 2026-03-06 | Joel M
ISM Africa | Make grant application |  | Done | 2026-03-06 | Ivy N
Lubona | Send financial model to investors (Norfund, etc) |  | Done | 2026-03-06 | Brenda C
Spitha | Complete financial model and share with client for their comments |  | Pending | 2026-03-06 | Susan B |  | Put on hold as we await a clear guidance due to demise of Job, Spitha founder
Wonderpac | Joel to follow up with the investor to issue a letter of intent |  | Done | 2026-03-06 | Joel M
Kakam Sarl | Get account access and complete their application in their behalf (the deadline is 2nd March 2026) |  | Dropped | 2026-03-06 | Brenda C
Ndivisi | Getting a lot of passes from investors due to the company’s loss. Update deck with the company's turnaround strategy |  | Done | 2026-03-06 | Irine M
Dr. Arunga | Send deal to the Christian based investor (Goodwell) |  | Done | 2026-03-06 | Irine M
Top Rich Motorcycles | Get 2025 accounts from the client (EADB requested for them) |  | Ongoing | 2026-03-06 | Ivy N |  | Reached out to Antony.
FitCiti | organize follow up call with Eugene from Africa50 |  | Done | 2026-03-06 | Duncan M |  | Investor passed on Sealtowers and FitCiti
Crown Healthcare | Follow up with client to pay NC’s invoice. Sheilla to follow up with the client on the CPs to unlock the 2nd tranche. Sheilla/Evans to follow up on the Nigerian deal |  | Done | 2026-03-06 | Sheilla W
Decca Medics | Update teaser with latest accounts and push investor engagements |  | Ongoing | 2026-03-06 | Cliff N
John Thuo Concept Note | Follow up to get feedback on the concept note. The client wants to give NC another assignment |  | Done | 2026-03-06 | Sheilla W
New deals | Imara and Savannah to be added to the live deal tracker |  | Done | 2026-03-06 | Brian B
Victoria Finance | Expand investor list (Check investors who put money into Rafode). Reactivate discussions with AlphaMundi |  | Done | 2026-03-06 | Irine M
Umoja MFI | Follow up to confirm if EQ finalized |  | Done | 2026-03-06 | Duncan M
Access Healthcare | Work on the CPs to unlock 2nd disbursement |  | Done | 2026-03-06 | Brenda C
KWFT | Evans to share discussions with Von Onyango on potential investors. They want to meet the client on Tue 4th |  | Done | 2026-03-06 | Brenda C
Deals | Sheilla & Brenda to share some deals with Susan, Solomon, Ivy, and Irine (KG Millers, Premier Zambia) |  | Done | 2026-03-06 | Evans W
Pearl Agro | Make grant application for AgriVentures. Update deck with 2025 a |  | Ongoing | 2026-03-06 | Brenda C
Brisk | Complete factsheet for the interested investor. |  | Done | 2026-03-06 | Cliff N
Melechizedek | Follow up on client payment |  | Done | 2026-03-06 | Cliff N
Steve Biko Strategy Assignment | Evans to follow up on the discussions |  | Pending | 2026-03-06 | Evans W
Savannah Hopsital | Arrange to have an in person meeting with the CFO within the week |  | Done | 2026-03-06 | Brian B
MyFugo | Irine to follow up on the deal and add it to the deal tracker |  | Done | 2026-03-06 | Irine M
Engagement Contract | Update NC engagement contract especially the retainer component to capture investor engagement. |  | Done | 2026-03-06 | Ken W
Redland Roses | The deal is from Adenia Capital and is trying to exit their stake. ACW is interested in a flower farm |  | Done | 2026-03-06 | Irine M |  | Client is yet to sign the contract. ACW passed on the deal.
Mara conservancy |  |  | Done | 2026-03-06 | Joel M
EAVCA | Pay for gala |  | Done | 2026-03-06 | Ken W
Fresh Kyenyanja | Close the account |  | Done | 2026-03-06 | Irine M
Florence Yula | Reach out on Family diet |  | Done | 2026-03-06 | Joel M
Volcano | Meeting with Yusuf |  | Done | 2026-03-06 | Joel M
Volcano | Send to Enabling Qapital |  | Done | 2026-03-06 | Joel M
Highland | Set up meeting with shona |  | Done | 2026-03-06 | Joel M
Volcano | Send to FCIA |  | Done | 2026-03-06 | Joel M
Branch | Evans to follow up on Branch as a potential client introduced by George of Mcredit |  | Done | 2026-03-06 | Evans W
09 March -13 March 2026
EFL | Complete factsheet for BlueOrchard | Monday Meeting | Done | 2026-03-13 | Duncan M |  | Sent partially completed form (80%) to Blue Orchard and also the client for their input
OYE | Joel and Evans to get historical accounts | Monday Meeting | Done | 2026-03-13 | Joel M
Kakam Sarl | Share deal with Kiva | Monday Meeting | Done | 2026-03-13 | Brenda C
Ndivisi | Share deal with investors who do trade financing | Monday Meeting | Done | 2026-03-13 | Irine M
Kuwekeza | Organize an intro call | Monday Meeting | Done | 2026-03-13 | Brian B
MCB | Send deal to Invest-in-Vision | Monday Meeting | Done | 2026-03-13 | Duncan M
Sealtowers | DM to follow up with Axian and other investors | Monday Meeting | Ongoing | 2026-03-13 | Duncan M
Yongeza | Cliff to follow up with GreenMax. Evans to send an email to Ventures Platform | Monday Meeting | Done | 2026-03-13 | Cliff N
DT Logistics | Clean up duplicate entry | Monday Meeting | Done | 2026-03-13 | Duncan M
Komarock Mordern | Evans to reach out to the CFO for updated financials | Monday Meeting | Done | 2026-03-13 | Evans W | Susan B | The management team have promised us that the FY25 audited accounts will be ready last week of March.
MetroConcepts | Adenia are interested in a site visit. Firm up on the arragements and update VDR | Monday Meeting | Done | 2026-03-13 | Irine M
FTG | Adenia are interested in a site visit. Firm up on the arragements and update VDR | Monday Meeting | Done | 2026-03-13 | Duncan M
Logistix Africa | Wants us to do a Pitch Deck | Monday Meeting | Done | 2026-03-13 | Irine M |  | Client is yet to sign the contract
Q1'2026 Review | DM to share the excel with the team members | Monday Meeting | Done | 2026-03-13 | Duncan M
Training | Sheilla to organize a training session to take team through the Appraisal Form | Monday Meeting | Done | 2026-03-13 | Sheilla W
Xtenda | Brian to follow up on the client to get data and firm up the engagement contract | Monday Meeting | Done | 2026-03-13 | Brian B
Fair Choice | Irine to follow up on the client to get data and firm up the engagement contract | Monday Meeting | Done | 2026-03-13 | Irine M |  | Client is yet to sign the contract
Impact Hub | Do a fee share agreement | Monday Meeting | Done | 2026-03-13 | Ivy N | Ken W
Branch MFI | Firm up meeting on Wednesday at Noblestride Capital Boardroom | Monday Meeting | Done | 2026-03-13 | Cliff N
GBRI Solutions (Eat Fresh) | Conduct financial analysis, prepare teaser and firm up call with client | Monday Meeting | Done | 2026-03-13 | Susan B
Marble Capital | Ivy to firm up meeting for Friday | Monday Meeting | Done | 2026-03-13 | Ivy N
Amana Bank Tz | Evans to follow up with Dennis for an engagement contract. Deal could be a good fit for Badea (Arab investor) | Monday Meeting | Dropped | 2026-03-13 | Evans W
Peoples Bank of Zanzibar | Evans to follow up with client for an engagement contract. Deal could be a good fit for Badea (Arab investor) | Verbal | Ongoing | 2026-03-13 | Evans W
Idman | Share deal with Badea | Verbal | Done | 2026-03-13 | Brian B |  | Request for Badea contacts from Evans
Sustainable Planet | Review pitchdeck and take lead of the transaction | WhatsApp | Done | 2026-03-13 | Irine M |  | Client is yet to sign the contract
Sustainable Planet | Prepare NDA and engagement contract | WhatsApp | Done | 2026-03-13 | Ken W | Irine M
PBZ Bank | Ken and Cliff to do an engagement contract | WhatsApp | Done | 2026-03-13 | Ken W
Jarine | Follow up on pending data | WhatsApp | Done | 2026-03-13 | Brian B
Deyabo | Client to sign contract |  | Done | 2026-03-13 | Ivy N
Lubona | Check with CFO on revised projections for the wider opportunity,2. We check with the client on valuation expectations. Phatisa can do both Debt and equity funding | WhatsApp | Done | 2026-03-13 | Brenda C
Mujuni | Ken to block calendar | WhatsApp | Done | 2026-03-13 | Ken W
Dennis Thuo | Sheilla do a follow up and share latest info. | WhatsApp | Done | 2026-03-13 | Sheilla W
Stan Chikakuda | Ivy to block calendar | WhatsApp | Done | 2026-03-13 | Ivy N
Sustainable Planet | Irine to have a look | WhatsApp | Done | 2026-03-13 | Irine M
Unigroup | Revise Invoice | WhatsApp | Done | 2026-03-13 | Ken W |  | Share with client
BRAMO TECH | Send NDA | WhatsApp | Done | 2026-03-13 | Ken W
Imara Mediplus | Add deal to Live Deals Tracker. Gather data and get started on the analysis & documentation | WhatsApp | Done | 2026-03-13 | Brian B
AfriCapital Deals | Assign deal leads for: 1. Mbasira Food Industries 2. Wakulima Agri Food Company Ltd 3. Project Reina – Uganda Largest FMCG Distributor 4. Tanzanian Investment Bank 5. KCG Aquatec Fish Farming Consultancy Co. Ltd | Other | Done | 2026-03-13 | Evans W
Dr. Arunga Eye Hospital | Firm up meeting with Clinton Health Access Initiative (CHAI) | WhatsApp | Done | 2026-03-13 | Irine M
16 March -19 March 2026 |  |  |  | 2026-03-19
Spiceword | Complete form from Cygnum Capital | Monday Meeting | Done | 2026-03-19 | Susan B
Spiceworld | Update teaser with spiceworld description (from Good Grains) | Monday Meeting | Done | 2026-03-19 | Susan B
New Paleah | client is slow to provide data. Evans to assist with follow ups | Monday Meeting | Done | 2026-03-19 | Brenda C
Oye | Follow up on data collection | Monday Meeting | Done | 2026-03-19 | Joel M
Kibinge | Follow up on data requests from investors | Monday Meeting | Done | 2026-03-19 | Cliff N
Coolcacth | Share deal with renew capital | Monday Meeting | Done | 2026-03-19 | Brian B
PURA | Update doc progress in the Live Deal tracker | Monday Meeting | Done | 2026-03-19 | Susan B
Dr. Arunga | Follow up on terms sheet from MCF | Monday Meeting | Done | 2026-03-19 | Irine M
Lakairo | Provide feedback to Qs from Tradeable | Monday Meeting | Ongoing | 2026-03-19 | Sheilla W
FTG | Firm up site visit with Adenia Capital | Monday Meeting | Done | 2026-03-19 | Duncan M
Valley Hospital | Expand investor list | Monday Meeting | Done | 2026-03-19 | Sheilla W
Yongeza | Expand investor list | Monday Meeting | Ongoing | 2026-03-19 | Cliff N
Decca Medics | Firm up meeting with the client. And also complete the Financial analysis and the teaser | Monday Meeting | Ongoing | 2026-03-19 | Cliff N
Komarock mordern | Follow up on the data requested by investors with the client | Monday Meeting | Done | 2026-03-19 | Susan B
AKM Glitters | Share a revised engagement contract | Monday Meeting | Done | 2026-03-19 | Brenda C | Ken W
Apicalmed | follow up with client on the 3 offers that are on the table | Monday Meeting | Done | 2026-03-19 | Susan B |  | Client did not pass BIO's DD. AGF-
Malipo | follow up with Bowmans on feedback from the investors the sent the deal to | Monday Meeting | Done | 2026-03-19 | Sheilla W
Classic Moulding | follow up with Peter of Blink Studio on signing of Letter of Intent | Monday Meeting | Done | 2026-03-19 | Joel M
Pearl Agro | Complete grant application ahead of the 30th March deadline | Monday Meeting | Dropped | 2026-03-19 | Brenda C
Highchem | follow up with AfricInvest on the ongoing DD | Monday Meeting | Done | 2026-03-19 | Sheilla W
NWH | Prioritize the documentation | Monday Meeting | Done | 2026-03-19 | Duncan M
AutoSprings | Follow up with client on the feedback on the Term sheet from Oxano Capital. Look at Talanton's TS to see if they mirrored it. Sheilla to firm up meeting with CEO | Monday Meeting | Done | 2026-03-19 | Sheilla W
Africa Inuka | follow up with Michael for data collection | Monday Meeting | Done | 2026-03-19 | Sheilla W
EldoTea | firm up meeting with Grounded VC (cannot postpone the meeting twice, that will be a red flag) | Monday Meeting | Dropped | 2026-03-19 | Brenda C
Logistix Africa | Complete pitch deck. | Monday Meeting | Done | 2026-03-19 | Irine M
Red Sea gateway terminals | share the proposal by EOD. The Financial model is due in 3 weeks. | Monday Meeting | Done | 2026-03-19 | Evans W | Cliff N
Bayport Tz | Review AFS and determine whether they meet Noblestride's thresshhold | WhatsApp | Done | 2026-03-19 | Susan B | Solomon O
23 March -27 March 2026 |  |  |  | 2026-03-27
Step Up Tech (Vision Plus) | Follow up on signing of engagement contract | Email | Done | 2026-03-27 | Ken W
Step Up Tech (Vision Plus) | Conduct financial analysis & prepare teaser | Email | Done | 2026-03-27 | Solomon O
SPICA Investment Management | Share invoice for USD 1,500 | Email | Dropped | 2026-03-27 | Ken W |  | Missalignment on the scope of work and fees payable
SPICA Investment Management | Allocate assignment on financial modelling and business plan preparation | Email | Dropped | 2026-03-27 | Evans W |  | Missalignment on the scope of work and fees payable
Lua Implementation | Provide feedback on Lua's automation proposal | Email | Done | 2026-03-27 | Solomon O | Evans W
Kijenge School Feeding Programme, Tz | Provide feedback on whether Noblestride is progressing with the fundraise discussions (USD 1 mn to implement their contract) | Email | Dropped | 2026-03-27 | Evans W | Solomon O
Mbasira and Chato Beverages, Tz | Review the two teasers and determine whether they meet Noblestride's thereshhold | Email | Done | 2026-03-27 | Solomon O | Ivy N
Eco Brix | Reach out to investors in the Iqo Brick investor folder | Monday Meeting | Done | 2026-03-27 | Irine M
Wakulima Foods | Complete deal entry in the live deal tracker | Monday Meeting | Done | 2026-03-27 | Ivy N
Mbasira Foods | Complete deal entry in the live deal tracker | Monday Meeting | Done | 2026-03-27 | Ivy N
TEV Africa | Complete deal entry in the live deal tracker | Monday Meeting | Done | 2026-03-27 | Ivy N
GBRI | Reach out to investors in the Six Square investor folder | Monday Meeting | Done | 2026-03-27 | Susan B
MCB | Confirm whether Michael Musau of Alterfin is open to meet with MCB during his Dar visist | Monday Meeting | Done | 2026-03-27 | Duncan M
E&M Tech | Set up a working meeting on Wed at Tatu City. Invite Solomon and tag Joel for Wonderpack | Monday Meeting | Done | 2026-03-27 | Duncan M
Progressive Credit | Set up physical meeting at client's premise | Monday Meeting | Done | 2026-03-27 | Joel M
Sunset Villa | Do a fee share agreement ... | Monday Meeting | Done | 2026-03-27 | Ken W | Susan B
Sidian Bank | Evans to meet with CEO Sidian to finalize on the contracting | Monday Meeting | Done | 2026-03-27 | Evans W | Brenda C
CoolCacth | Send deal to Iungo Capital and Shona Capital | Monday Meeting | Done | 2026-03-27 | Brian B
Wonderpac | Update teaser with the revised valuation expectation from the client | Monday Meeting | Done | 2026-03-27 | Joel M
E&M Tech | Expand investor list | Monday Meeting | Done | 2026-03-27 | Duncan M
SealTowers | Update entry on the live deal tracker | Monday Meeting | Done | 2026-03-27 | Duncan M
Fortune Credit | Evans to reach out to the CEO (Janet Kuteli) for a fundraising mandate | Monday Meeting | Done | 2026-03-27 | Evans W | Duncan M
Umoja International | Respond on the fees and maintain that NC can do 1% fee | Monday Meeting | Done | 2026-03-27 | Duncan M |  | Parties agreed to 0.75% given the quantum of funding needs
Apicalmed | Follow up on AGF, AfricInvest and Iungo offers | Monday Meeting | Done | 2026-03-27 | Susan B
Mbasira, Wakulima Foods, TEV Africa | Gather data and prepare teaser | Monday Meeting | Done | 2026-03-27 | Ivy N
Bramo Tech & Step Up Tech | Gather data and prepare teaser | Monday Meeting | Done | 2026-03-27 | Solomon O
TIB Tz | Confirm if AfriCapital has a signed mandate. Gather data and prepare teaser | Monday Meeting | Done | 2026-03-27 | Brian B |  | Followed up, will seek a mandate upon securing term sheet
Xtenda | Follow up on fee share agreement, in order to access to financials and other data | Monday Meeting | Done | 2026-03-27 | Brian B |  | Communication with the Zambian contact Twaambo is ongoing
Imara Mediplus | Prepare financial model | Monday Meeting | Ongoing | 2026-03-27 | Brian B |  | Done however client hasn't paid engagement fees
So Pure | Organize a call with Clement of Incoffin to understand what they need for the business plan | Monday Meeting | Done | 2026-03-27 | Susan B
Waridi Hotel | Update financial model with 2024 audited acccounts | Email | Done | 2026-03-27 | Irine M
Map FMCG Players | Map the supermarket chains shared on email. Create an excel and also try to check who are the owners/key management members | Email | Done | 2026-03-27 | Brian B
Case Hospital Ug | Follow up with Case | Monday Meeting | Ongoing | 2026-03-27 | Ivy N | Solomon O | I followed up on email. Waiting for response
30 March -2 April 2026 |  |  |  | 2026-04-02
Live Deal Tracker | Include a comlum(s) to track partial disbursments and the conditions to be met | Monday Meeting | Done | 2026-04-02 | Duncan M
Jarine | (1) Share full valuation report with James; (2) Update IM to 2025 audited + $3M scenarios (3) Update teaser to significant minority–majority; remove 70%; (4) Prepare and send to James: $3M scenarios (10–50% cash-out), board protections, Follow up with Daniel on 3–5yr sales plan, exit options after they review the cashout scenarios | Other | Done | 2026-04-04 | Brian B
7 April -10 April 2026 |  |  |  | 2026-04-10
The Fintech Company, Ug | Review teaser shared by joel_mutabazi@yahoo.com to determine if the company is a good fit for Noblestride | Email | Done | 2026-04-10 | Joel M
Project Tango_ MBO VDR | Ivy to gather data about the client, upload to VDR and share access link with Vantage Capital | Email | Done | 2026-04-10 | Ivy N
Kashia | Update valuation report with client's requests |  | Done | 2026-04-10 | Brenda C | Sheilla W
MetroConcepts | Check out ACME Containers and see if the two companies can be merged (Adenia Partners transaction) | Email | Ongoing | 2026-04-10 | Irine M
Progressive Capital | Share deal with Ironsharp (liaise with Brenda) | Monday Meeting | Done | 2026-04-10 | Joel M
Step Up SEZ | Share deals with EBRD and SPE Capital, and also shortlist a few more investors | Monday Meeting | Done | 2026-04-10 | Solomon O
Sunset Villa | The owner of Muthokinju is interested in the deal. | Monday Meeting | Done | 2026-04-10 | Susan B | Evans W
Kakam Sarl | Reach out to ODF to see if the are open to having an escrow account with the client to have visibility on use and flow of cash | Monday Meeting | Done | 2026-04-10 | Brenda C
Swift Credit | Follow up with CPF on the agreed disbursment of KES 250 million in tranches of KES 50 million | Monday Meeting | Ongoing | 2026-04-10 | Cliff N
Taimba | Organize a joint meeting with Oxano on the valuation | Monday Meeting | Done | 2026-04-10 | Brenda C
Tsavo Real Estate | Follow up with client to get contract signed and get started on the valuation assignment | Monday Meeting | Ongoing | 2026-04-10 | Brenda C | Evans W | The client has been unresponsive
Tesla Medical Centre | Follow up with client to get contract signed and get started on the advisory assignment | Monday Meeting | Pending | 2026-04-10 | Solomon O | Evans W | Hold until Gladwell reaches out
Amethis | Do a proposal to Frank Ndiyo to support Amethis acquire | Monday Meeting | Done | 2026-04-10 | Evans W
CPGT, Tanzania | Review deal to determine if it's a good fit for Noblestride | Email | Done | 2026-04-10 | Solomon O |  | Pass. Revenuie below 1M USD (102 k USD -2024, 64 K 2025 June) Looking to raise - 390,000 USD
Jerika Coffee, Rwanda | Review deal to determine if it's a good fit for Noblestride | Email | Done | 2026-04-10 | Solomon O
13 April -17 April 2026 |  |  |  | 2026-04-17
Umoja International | Update deal on the Live deal tracker. Conduct financial analysis, prepare teaser and shortlist investors | Monday Meeting | Done | 2026-04-17 | Duncan M
Sizwe | Update deal on the Live deal tracker. Conduct financial analysis, prepare teaser and shortlist investors | Monday Meeting | Done | 2026-04-17 | Sheilla W
Fair choice | Update deal on the Live deal tracker. Conduct financial analysis, prepare teaser and shortlist investors | Monday Meeting | Done | 2026-04-17 | Irine M
Forest Foods | Update deal on the Live deal tracker. Conduct financial analysis, prepare teaser and shortlist investors | Monday Meeting | Done | 2026-04-17 | Sheilla W
Karibu Loo | Send out teasers to investors and prepare financial model | Monday Meeting | Done | 2026-04-17 | Solomon O
Bramo Tech | Finalize teaser and shortlist investors | Monday Meeting | Done | 2026-04-17 | Solomon O
TEV Group Zambia | Gather data, conduct financial analysis, prepare teaser and shortlist investors | Monday Meeting | Done | 2026-04-17 | Joel M
Ravensus | Firm up meeting with Nedbank | Monday Meeting | Done | 2026-04-17 | Sheilla W
Balandi Kimeze | Finalize teasers and send out to investors. Prepare financial model and IM | Monday Meeting | Done | 2026-04-17 | Cliff N | Brian B
Kibinge | Finalize teasers and send out to investors. Prepare financial model and IM | Monday Meeting | Done | 2026-04-17 | Cliff N | Brian B
Wonderpac | Organize for a virtual meeting with the client on Wednesday the 15th April | Monday Meeting | Done | 2026-04-13 | Joel M
Soluti | Update teaser and send out deal to investors | Monday Meeting | Done | 2026-04-17 | Solomon O
Muhindi Mweusi | Expand investor list | Monday Meeting | Done | 2026-04-17 | Irine M
Tip Point Capital | Expand investor list to get more debt funding | Monday Meeting | Done | 2026-04-17 | Duncan M
Jarine | Focus on securing an offer from Talanton. Organize the a site visit/virtual call for the investor | Monday Meeting | Ongoing | 2026-04-17 | Brian B
VCB | Follow up with the VCB team for feedback on WaterEquity and Enabling Qapital | Monday Meeting | Done | 2026-04-17 | Duncan M
Brisk Credit | Follow up with Ezra of Seaf for an updated termsheet | Monday Meeting | Done | 2026-04-17 | Cliff N
NWH | Confirm the planned meeting with client | Monday Meeting | Done | 2026-04-17 | Duncan M
Afrika Inuka | Follow up with client for 2025 audited accounts and update pitchdeck | Monday Meeting | Done | 2026-04-17 | Sheilla W
Middle East Bank | Update teaser with equity ask and share deal with equity investors (do a valuation) | Monday Meeting | Done | 2026-04-17 | Duncan M
Maisha Bank | Follow up with client for signing of the mandate | Monday Meeting | Ongoing | 2026-04-17 | Cliff N | Ken W
Aviation Valuation | Follow up with client for signing of the mandate | Monday Meeting | Dropped | 2026-04-17 | Duncan M
Winnie | Get contact (email/phone) of Winnie from the KEPSA event. A potential investor for Classic Mouldings | Monday Meeting | Done | 2026-04-17 | Ivy N
SIMA Funds | Firm up meeting for Wednesday the 15th to discuss Victoria Finance Tz and EFL | Email | Done | 2026-04-14 | Irine M | Duncan M
Eat Fresh | Arrange a joint introductory call between client and Talanton this week on either Wednesday from 2pm, Thursday (10am - 1pm) and Friday (10am - 2pm). | Email | Done | 2026-04-17 | Susan B
Kashia | Update valuation report with client's requests | Email | Done | 2026-04-14 | Brenda C | Sheilla W
U&I MFI | Send to U&I bank CEO updated investor tracker and where we are with each investor | Email | Done | 2026-04-14 | Brenda C
VCB | Duncan to reach out to Andrew of Water Equity on revised term sheet | WhatsApp | Done | 2026-04-17 | Duncan M
Humphrey Watanga | Share draft PPT concept deck with Evans on Friday | Email | Done | 2026-04-17 | Ivy N | Joel M
U&I MFI | send to U&I bank CEO updated investor tracker | WhatsApp | Done | 2026-04-17 | Brenda C
Platinum Hopsitals Ug | Follow up on signing of engagement contract and latest data | WhatsApp | Done | 2026-04-17 | Duncan M
Sealtowers | Request for latest data from the management and re-do the valuation in a one-pager | WhatsApp | Done | 2026-04-17 | Duncan M
Sciencelab Limited Kenya | Organize an intro call with the client to understand their needs for Noblestride Services (Sell side advisory) | Email | Done | 2026-04-17 | Ken W | Cliff N
KTDA | Prepare a proposal to provide DD services for the acquisition of FERTIPLANT EAST AFRICA LIMITED. Deadline was 7th April 2026 | Email | Done | 2026-04-16 | Cliff N | Ken W
20 April -24 April 2026 |  |  |  | 2026-04-24
DT Logistics & DM's Deal | Firm up meeting with Stoa | Monday Meeting | Done | 2026-04-24 | Duncan M | Joel M | Meeting scheduled for 28th April
Sidian Bank | Send Accion's NDA with Sidian (Douglas) since theirs is not investor focused | Monday Meeting | Done | 2026-04-24 | Brenda C
Sidian Bank | Send Sidian Bank to IFC (Jesse) | Monday Meeting | Done | 2026-04-24 | Brenda C
Lubona | Follow up with the client to sign Norfund's termsheet | Monday Meeting | Ongoing | 2026-04-24 | Brenda C |  | We are waiting for Norfund to share the final term sheet for Lubona's execution
Ravensus | Focus efforts on Mirova (Martha) to provide a Termsheet | Monday Meeting | Ongoing | 2026-04-24 | Sheilla W
PURA | Get updates from client on the status of the loan refinancing from their bank | Monday Meeting | Done | 2026-04-24 | Susan B
Valley Hospital & Avenues | Prepare engagement contracts for the targets | Monday Meeting | Not started | 2026-04-24 | Evans W
Acorn Holdings | Mention Acorns planed Club deal to Nana and Sam of IFD (formerly IFU) | Monday Meeting | Done | 2026-04-24 | Duncan M
Nairobi River | Follow up with KCB on feedback from their IC on Friday and forwad feedback to CEEC | Monday Meeting | Done | 2026-04-24 | Duncan M
Easy Coach DD | Organize a call with the client | Monday Meeting | Dropped | 2026-04-24 | Evans W | Duncan M
Ryantel Systems | Follow up with client to get valuation assignment | Monday Meeting | Done | 2026-04-24 | Brenda C | Duncan M
Meliboat DD | Organize a call with the client | Monday Meeting | Done | 2026-04-24 | Brian B |  | Have Dr. Maxwel sign a mandate first. (Cliff and Ken- do 150k)
Sai Raj Ltd- Valuation | Follow up with the client to sign an NDA and request for historical data | Monday Meeting | Ongoing | 2026-04-24 | Ivy N | Duncan M | Follow up done. NDA nd Engagement Letter not signed yet.Client back on availability
Chemicaland- Fundraising | Follow up with the client to sign an NDA and request for historical data | Monday Meeting | Ongoing | 2026-04-24 | Solomon O | Sheilla W | Updated NDA shared with success and retainer payable on term sheet presentation
Meliboat Projections | Put in PPT | WhatsApp | Done | 2026-04-24 | Brian B
JOY MILLERS | add on the tracker of potential companies Joy Millers Ltd the company behind Raha | WhatsApp | Done | 2026-04-24 | Ken W
1. Bayer Foundation persons | Add on investor tracker | WhatsApp | Done | 2026-04-24 | Duncan M
2. UNCDF | Add on investor tracker | WhatsApp | Done | 2026-04-24 | Duncan M
Symon | Symon our NDA and list of initial data we require to evaluate the valuation assignment | WhatsApp | Done | 2026-04-24 | Brenda C
ICRA | please plan to pay | WhatsApp | Done | 2026-04-24 | Cliff N
Kigwa | do a high level data analysis for Kigwa Ridge School | WhatsApp | Ongoing | 2026-04-24 | Susan B |  | Audited Accounts to be shared
Kisumu Specialist Hospital | add Kisumu Specialist Hospital on the tracker they need projections | WhatsApp | Done | 2026-04-24 | Ken W
Talanton | write up on TZ to share with Cynthia of Talanton | WhatsApp | Done | 2026-04-24 | Susan B
Enwealth | evise the Enwealth Engagement contract and indicate that the success fee will be borne by the target company and not the Fund | WhatsApp | Done | 2026-04-24 | Cliff N
Lui Implementation | Schedule a call with Hillary to review Lui's contract | Verbal | Done | 2026-04-24 | Solomon O
Joy Millers | Get contacts for the potential client (Pipeline development) | Verbal | Ongoing | 2026-04-24 | Brenda C |  | I've reached out to my contact but I'm yet to get a response
*Norda Industries | Get contacts for the potential client (Pipeline development) | Verbal | Ongoing | 2026-04-24 | Susan B
Space and Style Ltd | Get contacts for the potential client (Pipeline development) | Verbal | Done | 2026-04-24 | Ivy N |  | Reached out to the assistant Naomi
27 April -30 April 2026 |  |  |  | 2026-04-30
FairChoice | Send MyCredit an NDA and share VDR access | Monday Meeting | Done | 2026-04-30 | Irine M
FairChoice | Get multiples for South African transactions | Monday Meeting | Done | 2026-04-30 | Irine M
Branch MFI | Put together documentation and pitch material (valuation report) for the Platinum Credit's acquisition plan | Monday Meeting | Done | 2026-04-30 | Brian B
Progressive | Send to MK Global | Monday Meeting | Done | 2026-04-30 | Joel M | Brenda C
EFL | Organize a call with the client to discuss Moringaway's TS | Monday Meeting | Done | 2026-04-30 | Duncan M
EFL | Write to Moringway team to explore using the subsidized FX hedging arrangement with TCX | Monday Meeting | Done | 2026-04-30 | Duncan M
Lubona | Share with Asif of Phatisa the financial model on WhatsApp | Monday Meeting | Done | 2026-04-27 | Brenda C
Boya | Send deal to Britam Lab | Monday Meeting | Done | 2026-04-30 | Brian B
Balandi Kimeze & Kibinge | Complete financial model | Monday Meeting | Done | 2026-04-30 | Cliff N | Brian B
Uganda Investment Authority | Write a letter of expression to support the companies in their portfolio | Monday Meeting | Done | 2026-04-30 | Brenda C
Access Beyond | Orgnaize a physical meeting with the client to check on them and understand the status od the business | Monday Meeting | Done | 2026-04-30 | Brenda C
Spectrum Credit (Swift Credit) | Follow up with CFP and the KCB (the custodian) to follow up on the remaining portion of the KES 50 million disbursement | Monday Meeting | Done | 2026-04-30 | Cliff N
Pezesha | Send to Best Seller | Monday Meeting | Done | 2026-04-30 | Cliff N
CPF | Send Fortune, Longitude and Marble Capital, and Edenbridge to CPF | Monday Meeting | Done | 2026-04-30 | Cliff N
AKM Glitters | Share a revised engagement contract and request for 2025 numbers | Monday Meeting | Done | 2026-04-27 | Brenda C | Ken W
Middle East Bank | Follow up with the client for signing of the revised contract | Monday Meeting | Done | 2026-04-30 | Ken W | Duncan M
Kisumu Specialist | Follow up on the signed contract | Monday Meeting | Done | 2026-04-30 | Ken W
Progressive Credit | Organize for a physical meeting with the CEO (Mbaabu) to sign the term sheet and get the pending data | Monday Meeting | Done | 2026-04-30 | Joel M
Ken | add Foodex on the tracker for USD 2Mn | WhatsApp | Done
4th -8th May 2026 |  |  |  | 2026-05-08
Douglas and Chege | Brenda to do an email |  | Done |  | Brenda C
Fund set up | Evans to follow up with Humphyrey
Fortune | Cliff to connect Susan |  | Done
Mujuni | Share the term sheet and schedule a call with Dickson. | WhatsApp | Done | 2026-05-08 | Ken W
11th May -15th May 2026 |  |  |  | 2026-05-15
Xodus Finance | Arrange for a call with Jelani for potential fundraise (Introduced on email by Doxa) | Email | Done | 2026-05-15 | Duncan M | Evans W | Jelani yet to confirm meeting slot
Science Lab | Return countersigned copy of the NDA and follow up on data & engagement contract | Email | Done | 2026-05-15 | Ken W | Cliff N
Mophones | Follow up on the action items from the Thurday call | Email | Done | 2026-05-15 | Ivy N
PASS Leasing Tz | Follow up on data and prepare teaser | Email | Not started | 2026-05-15 | Cliff N
KRS | Follow up on data from the client | Email | Done | 2026-05-15 | Susan B
AIS Capital | Firm up meeting with Leornad to discuss the land sale opportunity by Madison Insurance | Email | Ongoing | 2026-05-15 | Evans W | Duncan M
Sumuni Credit | Prepare an NDA and send to Stephen Marufu on WhatsApp +255 762 283 424 | Monday Meeting | Done | 2026-05-15 | Ken W
Kisumu Specialist Hospital | Share first draft of financial model by EOD 11th May 2026 | Monday Meeting | Ongoing | 2026-05-11 | Irine M | Brian B
Recommendation letters | Cliff and Solomon to get atleast 5 | Monday Meeting | Ongoing | 2026-05-15 | Cliff N | Solomon O | Irine
Noblestride Teams | Susan,Brian and Irine to do research | Monday Meeting | Done | 2026-05-15 | Brian B | Susan B
CBK Pensions- Jane Nzau | Evans and Duncan to share list to share with CBK pensions | Email | Done | 2026-05-15 | Evans W | Duncan M
Pivotech Ltd | Assess the financials to confirm if it is a good fit for Noblestride | Email | Done | 2026-05-15 | Susan B
Mophones | Conduct a Due Dilligence on the company. (Send deal to Shona Capital and Iungo Capital) | Monday Meeting | Ongoing | 2026-05-15 | Ivy N
Branch | y get info on the kes 250mn unallocated Capital on Branch. | WhatsApp | Done | 2026-05-15 | Brian B
ACEP senegal | Add on tracker | WhatsApp | Done | 2026-05-15 | Ken W
Khetias supermarket | Reach out to Manswowabe | WhatsApp | Done | 2026-05-15 | Sheilla W
Eat fresh | Susan to reach out on site visit | WhatsApp | Done | 2026-05-15 | Susan B
Zendawa | Arrange for an intro call between Sihafya and the management | Email | Done | 2026-05-15 | Brian B
Apicalmed | Arrange for an intro call between Sihafya and the management | Email | Ongoing | 2026-05-15 | Susan B |  | Client open for a call in mid June
18th May -22nd May 2026 |  |  |  | 2026-05-22
Amel Finance | Review data to determine whether the company is a good fit for Noblestride | Monday Meeting | Done | 2026-05-18 | Susan B
Foodex | Conduct financial analysis, prepare teaser and arrange intro call with client | Monday Meeting | Done | 2026-05-22 | Irine M
Access Bank | Follow up with the consultant to push through with the intro | Monday Meeting | Ongoing | 2026-05-22 | Brenda C
BSFI Tz | Follow up on NDA and data collection | Monday Meeting | Done | 2026-05-22 | Duncan M
Jarine | Send impact report to Talanton | Monday Meeting | Done | 2026-05-18 | Brian B
Jarine | Firm up meeting with DOB Equity | Monday Meeting | Done | 2026-05-18 | Brian B
Lubona | Follow up on the final term sheet from Norfund and fill in the KYC | Monday Meeting | Ongoing | 2026-05-22 | Brenda C
MEB, VCB | Follow up with Lefteris Ngugi on Kohtla's EoIs. | WhatsApp | Done | 2026-05-20 | Sheilla W
Kakam Sarl | Introduce Guy Eddy to Crown Healthcare and Sphinx Pharmaceuticals. | WhatsApp | Done | 2026-05-18 | Sheilla W
Engagment Contracts Tracker | Update tracker to have complete records | Email | Ongoing | 2026-05-22 | Ken W
Central Storage | - Addition of the deal to the Live Deal Tracker - Financial analysis - Teaser preparation - Kick off meeting with the client - Potential investor shortlist - VDR setup | Email | Ongoing | 2026-05-29 | Joel M
Eldo Tea - | Judith Ngonyo is asking about what happened to Eldo Tea - please update her tomorrow - give caroline one more call | WhatsApp | Ongoing | 2026-05-22 | Brenda C
Fortune Credit | share their current covenants, lender fees plus relevant withholding tax and dividend policy | WhatsApp | Ongoing | 2026-05-22 | Susan B |  | Got dividend policy on Friday. 22nd May 2026. Waiting for the rest of the information
Mophones. | Nabo Capital are keen on Mophones. Check mail | WhatsApp | Done | 2026-05-22 | Ivy N
Lubona | Inform team we go slow on Phatisa and AfricInvest. Let's focus on Norfund and Bio invest | WhatsApp | Done | 2026-05-22 | Brenda C | Brenda C
CIB Bank | on the call with CIB Bank ask if they can issue SBLC | WhatsApp | Done | 2026-05-22 | Duncan M
Isaac DT Logistics | please check with Isaac DT Logistics if he can get an SBLC | WhatsApp | Ongoing | 2026-05-22 | Joel M
Yongeza | update Josh on the progress |  | Not started
Sustainable Planet | Update client on Progress | WhatsApp | Done | 2026-05-22 | Irine M |  | I already reached out to the client and discussed the terms oif the termsheet shared by Sayuni. He mentioned he will have to discuss with KWAL first to align since the termsheet is pegged on the contract that the client ahs with KWAL.
MCB | Send to Triodos | WhatsApp | Done | 2026-05-22 | Duncan M
AECF | following up on their NDA to Progressive | WhatsApp | Ongoing | 2026-05-22 | Joel M
Adenia team | reach out to Adenia team on Redland roses | WhatsApp | Done | 2026-05-22 | Ivy N
MyCredit and Admaius. | follow up on next steps for MyCredit and Admaius. | WhatsApp | Ongoing | 2026-05-22 | Duncan M
25th May -29th May 2026 |  |  |  | 2026-05-29
Amel Finance | - Addition of the deal to the Live Deal Tracker - Financial analysis - Teaser preparation - Kick off meeting with the client - Potential investor shortlist - VDR setup | Email | Not started | 2026-05-29 | Joel M
Apollo Tours | - Addition of the deal to the Live Deal Tracker - Financial analysis - Teaser preparation - Valuation Report - Kick off meeting with the client - Potential investor shortlist - VDR setup | Email | Ongoing | 2026-05-29 | Brian B
Blue orchard | Call Njeri Ng'ang'a | Monday Meeting | Not started | 2026-05-29 | Brenda C
Progressive | Go to progressive to collect the NDA | Monday Meeting | Not started | 2026-05-29 | Joel M
Savannah Hospital | Request the client to send their valuation report to C-care | Monday Meeting | Not started | 2026-05-29 | Brian B
Formulas:
Deadline = [Deadline, row above]

## Lists (hidden)
Status | Deal Lead | Source
Done | Brenda C | Monday Meeting
Ongoing | Brian B | WhatsApp
Pending | Cliff N | Email
Not started | Duncan M | Verbal
Dropped | Evans W | Other
Irine M
Ivy N
Joel M
Ken W
Sheilla W
Solomon O
Susan B